## Sheet1
Conclave Backdater
Action Item | Due Date | Person Responsible | Compeleted
Date Selected | -400 | Council of Chiefs
Host Lodge Chosen | -400 | Council of Chiefs
Section Officers Elected | -365 | Conclave Participants
Location Finalized | -365 | Council of Chiefs
Conclave Vice Chiefs Filled | -350 | Section Chief
Budget Proposed | -300 | Section Chief
Theme Ideas Proposed | -300 | At Large
Theme Chosen w/ Branding | -275 | Communications CVC
Schedule Draft 1 | -275 | Section Vice Chief
Activities Chosen | -250 | CVCs
Training Chosen | -250 | Training CVC
Shows Script Draft 1 | -250 | Shows CVC
Menu Draft | -250 | Host Lodge
Final Schedule | -225 | Section Chief
Final Menu | -225 | Host Lodge
Registration Opens | -200 | Section Staff Adviser
Trainers Chosen | -200 | Training CVC
Needs Lists Turned In | -200 | CVCs
Final Shows Script | -200 | Shows CVC
Conclave Report Filled | 30 | Outgoing Section Chief
*Note: Planning with 100 days left allows for adjustments to be made.